TAYO  /  PRODUCT REFERENCE

Default Filipino Wedding Template

The comprehensive opt-out checklist that loads when a couple creates a wedding event in Tayo V1.

Document version: v1.0 — May 2026

Status: Confidential — Product Reference

# Introduction

This document defines the canonical default checklist that auto-loads when a Filipino couple creates a wedding event in Tayo V1. The design philosophy is comprehensive defaults with explicit opt-out: every category, vendor type, legal requirement, ceremony role, and post-wedding task that applies to a typical Filipino-Catholic wedding (church ceremony + hotel reception) appears by default. Couples remove what doesn't apply to their event rather than starting from scratch.

This template was developed by cross-referencing public Philippine wedding checklists (Kasal.com, EventNest, Bride and Breakfast, Storia, FilipiKnow, Nuptials.ph, Shangri-La Boracay) against the founding couple's actual wedding planning artifacts (Buanhog-Casasola, December 18, 2026) including their budget tracker, vendor contracts (10 documents totaling P2.56M), planning timeline, and guest list. Items marked REQUIRED are essential for a Catholic church wedding to legally and ceremonially proceed. Items marked DEFAULT are loaded by default but can be removed. Items marked OPTIONAL appear in the catalog but require the couple to opt in.

# Section 1 — Legal & Religious Requirements

These items are non-negotiable for a Catholic church wedding to be legally valid in the Philippines. They appear as REQUIRED tasks in the timeline; couples cannot remove them, only mark as 'in progress' or 'completed.'

| Item | Lead time | Notes | Default Status |
| --- | --- | --- | --- |
| Pre-Cana / Discovery Weekend / Marriage Seminar | 6+ months | Parish-administered; varies by diocese | REQUIRED |
| Canonical Interview | 4–6 months | Couple meets parish priest one-on-one | REQUIRED |
| Baptismal Certificate (both parties) | 6+ months | Must be recent (within 6 months of wedding) | REQUIRED |
| Confirmation Certificate (both parties) | 6+ months | From confirming parish | REQUIRED |
| CENOMAR (Certificate of No Marriage Record) | 3+ months | From PSA, valid for 6 months | REQUIRED |
| PSA Birth Certificate (both parties) | 3+ months | Latest copy required | REQUIRED |
| Marriage License | 1 month | 10-day cooling period after submission; valid 120 days | REQUIRED |
| Officiant fee / mass donation | Pay before wedding | Varies by parish (P5,000–P20,000 typical) | REQUIRED |
| Banns of Marriage | Pre-ceremony | Parish-posted notice, 3 weeks | REQUIRED |
| Civil Marriage License (Local Civil Registrar) | 1 month | Required even if civil ceremony precedes church | REQUIRED |

# Section 2 — Pre-Wedding Events

Optional but commonly planned events surrounding the wedding day. Couples toggle these on or off based on what they want to host.

| Event | Typical lead time | Default Status | Notes |
| --- | --- | --- | --- |
| Pamamanhikan (formal proposal to bride's family) | 6–12 months | DEFAULT | Traditional Filipino formality |
| Engagement party | 6–12 months | OPTIONAL | Often combined with pamamanhikan |
| Pre-nup photo shoot | 3–6 months | DEFAULT | Standard PH practice; usually bundled with photographer package |
| Pre-nup video / Save-the-Date video | 3–6 months | DEFAULT | Often bundled with prenup |
| Save-the-date cards | 6–9 months | DEFAULT | Digital and/or printed |
| Bridal shower / despedida de soltera | 1–2 months | OPTIONAL | Bride's friends host |
| Stag party / bachelor party | 1–2 months | OPTIONAL | Groom's friends host |
| Catholic retreat / couple retreat | 6+ months | OPTIONAL | Some parishes require Discovery Weekend specifically |
| Wedding rehearsal | 1 day | DEFAULT | Usually church-led, day before wedding |
| Rehearsal dinner | 1 day before | OPTIONAL | Common but not universal in PH |

# Section 3 — Attire

## 3.1 Couple

| Item | Lead time | Default Status | Notes |
| --- | --- | --- | --- |
| Bridal gown + veil + train | 6+ months | DEFAULT | Custom/made-to-order standard |
| Bridal shoes | 3 months | DEFAULT |  |
| Bridal jewelry / accessories | 3 months | DEFAULT |  |
| Wedding ring (bride) | 2–4 months | REQUIRED |  |
| Wedding ring (groom) | 2–4 months | REQUIRED |  |
| Engagement ring (if not yet purchased) | as needed | OPTIONAL |  |
| Groom suit / barong tagalog | 3+ months | DEFAULT |  |
| Groom shoes / accessories | 2 months | DEFAULT |  |

## 3.2 Entourage Attire

Couples typically coordinate but can opt out per role.

| Item | Lead time | Default Status | Notes |
| --- | --- | --- | --- |
| Maid of Honor gown | 3 months | DEFAULT |  |
| Best Man suit / barong | 3 months | DEFAULT |  |
| Bridesmaids gowns | 3 months | DEFAULT |  |
| Groomsmen suits / barongs | 3 months | DEFAULT |  |
| Flower girl dresses | 2 months | DEFAULT |  |
| Ring bearer outfit | 2 months | DEFAULT |  |
| Bible bearer outfit | 2 months | DEFAULT |  |
| Coin (arras) bearer outfit | 2 months | DEFAULT |  |
| Mothers' attire (both) | 3 months | DEFAULT |  |
| Fathers' attire (both) | 3 months | DEFAULT |  |
| Principal sponsors (Ninongs/Ninangs) attire | 2 months | OPTIONAL | Often DIY by sponsors themselves |
| Secondary sponsors attire | 2 months | OPTIONAL |  |

# Section 4 — Vendor Categories

These are the canonical vendor categories. Each comes pre-loaded with a 'Browse Tayo Recommended' link, a 'Add my own vendor' option, and a 'Mark as DIY' toggle. Couples remove categories that don't apply (e.g., a couple having a beach wedding wouldn't need 'choir').

## 4.1 Ceremony

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Church / ceremony venue | REQUIRED |  |
| Officiant / priest fees | REQUIRED |  |
| Mass coordinator | OPTIONAL | Some parishes provide; otherwise hire one |
| Choir / mass musicians | DEFAULT | Often parish-provided; can be replaced with Quartet |
| Ceremony flowers (altar, aisle, decor) | DEFAULT |  |
| Bridal bouquet | DEFAULT |  |
| Bridesmaids bouquets | DEFAULT |  |
| Mothers' corsages | DEFAULT |  |
| Groomsmen boutonnieres | DEFAULT |  |
| Sponsors' boutonnieres / corsages | DEFAULT |  |
| Aras coins | DEFAULT |  |
| Cord, veil, candle props | DEFAULT |  |
| Ring pillow | DEFAULT |  |
| Bible / Misa Lente | DEFAULT |  |
| Misalette / printed program | DEFAULT |  |

## 4.2 Reception

Where bundled hotels apply.

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Reception venue | REQUIRED |  |
| Catering / food & beverage | REQUIRED | Often bundled with hotel venue |
| Bar service / mobile bar | DEFAULT | Or covered by venue corkage |
| Wedding cake | REQUIRED | Often bundled with hotel; can be swapped for outside baker |
| Cake table styling | DEFAULT |  |
| Centerpieces / table flowers | DEFAULT |  |
| Reception styling / decor | DEFAULT |  |
| Lights & sound | REQUIRED |  |
| LED wall / projector / livefeed | DEFAULT | Bundled or separate AV vendor |
| Live band / quartet | DEFAULT |  |
| DJ / spinner | DEFAULT |  |
| Host / MC / emcee | DEFAULT |  |
| Photobooth | DEFAULT |  |
| Photoman / photo strip booth | OPTIONAL |  |
| Glambooth / 360 camera | OPTIONAL |  |
| Magazine / Vogue print | OPTIONAL |  |
| Coffee bar | OPTIONAL |  |
| Perfume bar | OPTIONAL |  |
| Massage booth | OPTIONAL |  |
| Food cart vendors (potato corner, putobumbong, donut, churros) | OPTIONAL |  |
| Grazing table | OPTIONAL |  |
| Lechon | OPTIONAL |  |
| Fireworks / sparklers | OPTIONAL |  |
| Interactive game booth | OPTIONAL |  |
| Souvenir booth | OPTIONAL |  |
| Mobile bar (additional) | OPTIONAL |  |

## 4.3 Photo & Video

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Wedding day photographer | REQUIRED |  |
| Wedding day videographer | DEFAULT | Often bundled with photographer |
| Same-day edit (SDE) video | DEFAULT |  |
| Drone / aerial coverage | DEFAULT |  |
| Live streaming | OPTIONAL | For distant family |
| Pre-nup photographer | DEFAULT | Usually bundled |
| Pre-nup videographer | DEFAULT |  |
| Wedding photo album / photobook | DEFAULT |  |
| Photo prints / blow-ups | DEFAULT |  |
| Highlight reel | DEFAULT |  |

## 4.4 Hair & Makeup

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Bride wedding-day HMUA | REQUIRED |  |
| Bride pre-nup HMUA | DEFAULT |  |
| Groom grooming | DEFAULT | Usually included in bride's package |
| Mothers HMUA | DEFAULT |  |
| Maid of Honor / Bridesmaids HMUA | DEFAULT |  |
| Sisters / extended entourage HMUA | OPTIONAL |  |
| Hair extensions rental | OPTIONAL |  |

## 4.5 Coordination & Planning

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Wedding planner / coordinator | DEFAULT |  |
| Halfway planner | OPTIONAL | Couples often start full planning then hand off |
| On-the-day coordinator | REQUIRED | Even DIY weddings need a day-of point person |
| Stylist (separate from coordinator) | OPTIONAL |  |
| Choreographer (for couples wanting choreographed first dance) | OPTIONAL |  |

## 4.6 Logistics & Transport

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Bridal car | DEFAULT | Often bundled with hotel |
| Coaster / entourage transport | DEFAULT |  |
| Special transport (elderly grandparents, etc.) | OPTIONAL |  |
| Hotel rooms for couple's prep | DEFAULT | Often venue-bundled |
| Hotel rooms for parents | DEFAULT |  |
| Hotel rooms for entourage | OPTIONAL |  |
| Hotel rooms for out-of-town family | OPTIONAL |  |

## 4.7 Stationery & Print

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Save-the-date | DEFAULT |  |
| Wedding invitations (digital) | REQUIRED |  |
| Wedding invitations (print) | DEFAULT |  |
| RSVP cards | DEFAULT | Or digital RSVP via Tayo |
| Wedding program / mass missalette | DEFAULT |  |
| Menu cards | DEFAULT |  |
| Place cards / table cards | DEFAULT |  |
| Table numbers | DEFAULT |  |
| Welcome signage | DEFAULT |  |
| Direction signage | OPTIONAL |  |
| Thank-you cards | DEFAULT |  |
| Calligraphy / hand-lettering | OPTIONAL |  |

## 4.8 Favors & Gifts

| Vendor Category | Default Status | Notes |
| --- | --- | --- |
| Guest favors / souvenirs | DEFAULT |  |
| Sponsor gifts (Ninong / Ninang) | DEFAULT |  |
| Entourage gifts | DEFAULT |  |
| Parent gifts | DEFAULT |  |
| Officiant gift | DEFAULT |  |
| Vendor tips budget | DEFAULT |  |

# Section 5 — Filipino-Catholic Ceremony Specifics

## 5.1 Ceremony Roles

People, not vendors. Each role gets a guest assignment field. Required roles must be filled before wedding day; optional ones can be skipped.

| Role | Default Status |
| --- | --- |
| Bride | REQUIRED |
| Groom | REQUIRED |
| Father of the bride (giving away) | DEFAULT |
| Mother of the bride | DEFAULT |
| Father of the groom | DEFAULT |
| Mother of the groom | DEFAULT |
| Maid of Honor (1+) | DEFAULT |
| Best Man (1+) | DEFAULT |
| Bridesmaids | DEFAULT |
| Groomsmen | DEFAULT |
| Principal sponsors — Ninongs (typically 7+) | REQUIRED for Catholic |
| Principal sponsors — Ninangs (typically 7+) | REQUIRED for Catholic |
| Secondary sponsors — Cord (1 pair) | DEFAULT |
| Secondary sponsors — Veil (1 pair) | DEFAULT |
| Secondary sponsors — Candle (1 pair) | DEFAULT |
| Flower girls (1+) | DEFAULT |
| Ring bearer | DEFAULT |
| Bible bearer | DEFAULT |
| Coin (arras) bearer | DEFAULT |
| 1st reading | DEFAULT |
| 2nd reading | DEFAULT |
| Responsorial Psalm | DEFAULT |
| Prayers of the Faithful | DEFAULT |
| Communion ministers | OPTIONAL |

## 5.2 Reception Activities

Program flow.

| Activity | Default Status | Notes |
| --- | --- | --- |
| Couple's grand entrance | DEFAULT |  |
| First dance | DEFAULT |  |
| Couple's introduction | DEFAULT |  |
| Parent dances (mother-son, father-daughter) | DEFAULT |  |
| Toast / champagne ceremony | DEFAULT |  |
| Cake cutting + feeding | DEFAULT |  |
| Cake trinkets / cake pulls (Filipino tradition) | DEFAULT |  |
| Best Man / Maid of Honor speeches | DEFAULT |  |
| Parent speeches | DEFAULT |  |
| Money dance / panyo dance | DEFAULT |  |
| Prosperity dance (couples invited, money rains) | DEFAULT |  |
| Bouquet toss | DEFAULT |  |
| Garter toss | OPTIONAL | Less common in PH |
| Wine ceremony / unity ritual | OPTIONAL |  |
| Send-off (sparklers, bubbles, etc.) | DEFAULT |  |

# Section 6 — Day-Of Run-of-Show

This section pre-loads the canonical 30-row hour-by-hour timeline (matching the BBB sheet from the Buanhog-Casasola wedding). Couples customize times based on their venue and ceremony schedule.

| Time | Duration | Activity | Default Status |
| --- | --- | --- | --- |
| 7:15 AM | 0:45 | Hair and makeup artists arrive | DEFAULT |
| 8:00 AM | 1:00 | Hair and makeup appointments begin | DEFAULT |
| 9:00 AM | 1:00 | Food and drinks delivered to wedding party | DEFAULT |
| 10:00 AM | 1:15 | Wedding dress steam / photographer arrives | DEFAULT |
| 11:15 AM | 0:30 | Wedding party finishes getting ready | DEFAULT |
| 11:45 AM | 0:15 | Bride puts on dress | DEFAULT |
| 12:00 PM | 0:15 | First look with parents | DEFAULT |
| 12:15 PM | 0:15 | Wedding party portraits | DEFAULT |
| 12:30 PM | 0:30 | Ceremony setup | DEFAULT |
| 1:00 PM | 0:15 | Pre-ceremony music begins | DEFAULT |
| 1:15 PM | 0:15 | Family photos | DEFAULT |
| 1:30 PM | 0:05 | Wedding party departs for ceremony | DEFAULT |
| 1:35 PM | 0:15 | Guests arrive at the ceremony | DEFAULT |
| 1:50 PM | 0:10 | Couple arrives with parents at ceremony | DEFAULT |
| 2:00 PM | 1:00 | Ceremony begins | DEFAULT |
| 3:00 PM | 0:10 | Ceremony ends | DEFAULT |
| 3:10 PM | 0:20 | Transportation for guests to reception | DEFAULT |
| 3:30 PM | 0:30 | Couple photos at ceremony location | DEFAULT |
| 4:00 PM | 0:30 | Cocktail hour begins | DEFAULT |
| 4:30 PM | 1:30 | Reception begins | DEFAULT |
| 6:00 PM | 0:25 | Couple introduction and first dance | DEFAULT |
| 6:25 PM | 0:05 | Parent speech | DEFAULT |
| 6:30 PM | 0:20 | Dinner first course served | DEFAULT |
| 6:50 PM | 0:35 | Best man and maid of honor speeches | DEFAULT |
| 7:25 PM | 0:20 | Dinner second course served | DEFAULT |
| 7:45 PM | 0:15 | Parent dances | DEFAULT |
| 8:00 PM | 0:30 | Dancing begins | DEFAULT |
| 8:30 PM | 1:00 | Dessert course served | DEFAULT |
| 9:30 PM | 2:00 | Cake cutting | DEFAULT |
| 11:30 PM | — | Reception ends | DEFAULT |

# Section 7 — Post-Wedding Tasks

Most apps and most couples forget this entirely. Tayo loads these as a post-event checklist that activates on the wedding date.

| Task | Timing | Default Status |
| --- | --- | --- |
| Send thank-you cards to sponsors and key vendors | 1–2 weeks after | DEFAULT |
| Collect marriage certificate from officiant or LCR | 1–2 weeks after | REQUIRED |
| Wait for PSA encoding | 2–3 months | REQUIRED |
| Request PSA marriage certificate | 3–4 months after | REQUIRED |
| Update PSA / Civil Registry records | 4 months | DEFAULT (if surname change) |
| Update passport | 1 month after PSA cert | DEFAULT (if surname change) |
| Update bank accounts | 1 month after PSA cert | DEFAULT (if surname change) |
| Update SSS records | 1 month after PSA cert | DEFAULT (if surname change) |
| Update PhilHealth records | 1 month after | DEFAULT |
| Update Pag-IBIG records | 1 month after | DEFAULT |
| Update BIR records (TIN) | 1 month after | DEFAULT |
| Update driver's license | 1 month after | DEFAULT |
| Update voter registration | within 1 year | OPTIONAL |
| Update insurance beneficiaries | 1 month after | REQUIRED |
| Update credit card / financial accounts | 1 month after | DEFAULT |
| Settle remaining vendor payments | within 30 days | REQUIRED |
| Receive wedding album from photographer | 4–6 months after | TRACK |
| Receive highlight reel | 2 weeks (SDE) / 1–3 months (full) | TRACK |
| Anniversary planning | annually | OPTIONAL |

# Section 8 — Default Budget Categories (PHP)

Pre-loaded budget categories with typical PH cost ranges. Couples adjust based on their actual budget and bookings. Extracted from the founding couple's budget tracker plus PH averages.

| Category | Typical Range (PHP) | Notes |
| --- | --- | --- |
| Church / ceremony venue | P20,000–P50,000 |  |
| Reception venue + catering | P500,000–P1,500,000 | Often bundled |
| Photographer + videographer | P100,000–P250,000 |  |
| Coordinator | P50,000–P150,000 |  |
| Bridal gown | P100,000–P300,000 |  |
| Groom suit / barong | P30,000–P80,000 |  |
| HMUA (bride + entourage) | P40,000–P100,000 |  |
| Lights & sound + LED | P50,000–P150,000 |  |
| Stylist / decor | P150,000–P500,000 |  |
| Live music | P25,000–P60,000 |  |
| DJ / host | P20,000–P50,000 |  |
| Florist (beyond bundle) | P30,000–P100,000 |  |
| Bridal car | P10,000–P30,000 | Often c/o couple or hotel-bundled |
| Coaster / entourage transport | P15,000–P30,000 |  |
| Wedding rings | P30,000–P150,000 |  |
| Invitations + stationery | P20,000–P60,000 |  |
| Favors / souvenirs | P30,000–P100,000 |  |
| Sponsor gifts | P30,000–P90,000 |  |
| Specialty stations (coffee bar, perfume bar, etc.) | P20,000–P100,000 each |  |
| Pre-nup shoot (separate) | P25,000–P100,000 |  |
| Crew meals (vendor staff) | P500/head x ~30 staff = P15,000 typical |  |
| Officiant / mass donation | P5,000–P20,000 |  |
| Tips / contingency | 5–10% of total budget |  |

# Section 9 — How This Maps to Tayo V1 UX

When a couple creates a wedding event in Tayo:

- They enter basic info: names, date, location, ceremony type (Catholic / civil / non-denominational), venue type (hotel / garden / beach / other), guest count estimate.

- Tayo loads this entire default template into their account.

- Required items appear with a red asterisk and cannot be deleted.

- Default items appear with a check mark and a 'Remove from my wedding' option.

- Optional items appear under 'Available add-ons' with a 'Add to my wedding' toggle.

### Each vendor category has three actions

- 'Browse Tayo Recommended' — opens directory filtered to category

- 'Add my own vendor' — couple enters info, triggers Tayo recruitment outreach

- 'Mark as DIY / Family' — covered by family/friends, no vendor needed

- 'Remove from my wedding' — for irrelevant categories

### Each task item shows

- Suggested timeline (when to start)

- Lead time / due date relative to wedding date

- Status (not started / in progress / completed)

- Assigned-to (which person — couple, coordinator, family member)

### Progress tracking

The app shows progress: '12 of 47 default tasks completed, 34 to go.'

This template is the V1 baseline. It will evolve based on real couple usage. Couples planning non-Catholic, civil, beach, destination, or non-traditional weddings should be presented with adapted versions of this template (V1.5+).